## Intro
| Market Renewal Program - Readiness Checklist for Market Participants |  |  | This page NOT visible to MPs (everything to right of green line) |  |  | Date: | 2023-03-29
|  |  |  | See also hidden tab called "Dropdowns" |  |  | Version #: | 1
Welcome to the Market Participant Readiness Checklist for the IESO’s Market Renewal Program (MRP). MRP has been engaged with stakeholders and market participants on the design of the renewed market, and is now engaging participants through education and training prior to MRP in-service in May, 2025. Market participants will need to undertake a number of activities to prepare for the renewed market. This checklist will guide Market Participants on the testing, training and educational tasks that each participant should consider completing, and will assist participants in beginning to plan and resource these, and to assess the business processes changes needed within each organization. Each participant can choose their segment (or segments) here below and have a tailored list of testing and training activities relevant to their participation type. The checklist will link directly to the relevant training products, when available, and is a place for participants to track their progress. Hovering over the red comment triangles in the column headings provides additional information. Most importantly, the IESO is here to work with you to ensure all participants are ready for the launch of the renewed market.
If you are unclear about any of these checklist tasks, or require IESO assistance with any questions arising from the information below, please reach out to market.renewal@ieso.ca to be connected with the Participant Readiness support team.
Organization Name: |  | Rights Admin Name:
Organization Short Name: |  | MRP Contact Person:
Market Registration #:
Market Participation Segments (click all that apply now/may apply in future to your Organization, currently and under MRP):
| (Note: Each time you add or remove a segment category here, you must also click on the Checklist Tab, select the Down Arrow in the top right corner, marked "Segment Filter Update", then click OK, in order to show or hide additional tasks for that Market Segment category.) |  |  |  |  | Note: Nuclear non-dispatch is disabled here; there are no current MPs in this group.
|  |  |  | ÿ Natural Gas/Oil Generator (dispatchable, including NQS) | TRUE | ÿ Electricity Storage Resource (dispatchable) | TRUE | ÿ Ancillary Service Provider | TRUE
|  |  |  | ÿ Natural Gas/Oil Generator (non-dispatchable) | TRUE | ÿ Electricity Storage Resource (self-scheduling) | TRUE | ÿ Transmission Rights Participant | TRUE
|  |  |  | ÿ Biogas/Biomass Generator (dispatchable, including NQS) | TRUE | ÿ Local Distribution Company | TRUE | ÿ Other Market Participant role | TRUE
|  |  | New Roles you are considering/intending: | ÿ Biogas/Biomass Generator (non-dispatchable) | TRUE | ÿ Transmission Company | TRUE
|  |  |  | ÿ Hydroelectric Generator (dispatchable) | TRUE | ÿ Dispatchable Load | TRUE | New Roles you are considering/intending:
|  |  |  | ÿ Hydroelectric Generator (non-dispatchable) | TRUE | ÿ Non Dispatchable Load | TRUE | ÿ Price Responsive Load | TRUE
|  |  |  | ÿ Wind/Solar Generator (dispatchable) | TRUE | ÿ Hourly Demand Response | TRUE | ÿ Virtual Transaction Energy Trader | TRUE
|  |  |  | ÿ Wind/Solar Generator (non-dispatchable) | TRUE | ÿ Intertie Trader (Imports and Exports) | TRUE | ÿ Adding a new Participation Segment or Resource during the 2023-2025 preparation period (check also the applicable segment) | TRUE
|  |  | Version 1.0 - March 29, 2023 | ÿ Nuclear Generator(dispatchable) | TRUE | ÿ Nuclear Generator (non-dispatchable) | FALSE
Natural Gas/Oil Generator (dispatchable, including Non Quick Start (NQS))
Natural Gas/Oil Generator (non-dispatchable)
Biogas/Biomass Generator (dispatchable, including Non Quick Start (NQS))
Biogas/Biomass Generator (non-dispatchable)
Hydroelectric Generator (dispatchable)
Hydroelectric Generator (non-dispatchable)
Nuclear Generator (dispatchable)
Wind/Solar Generator (dispatchable)
Wind/Solar Generator (non-dispatchable)
Electricity Storage Resource (dispatchable)
Electricity Storage Resource (non-dispatchable)
Local Distribution Company (LDC)
Transmission Company
Dispatchable Load (DL)
Non Dispatchable Load (NDL)
Hourly Demand Response (HDR)
Intertie Trader (Imports and Exports)
Ancillary Service Provider (ASP)
Transmission Rights Participant (TR)
Other Market Participant role
Price Responsive Load (PRL)
Virtual Trader (VT)
Adding a new Participation Segment or Resource during the 2023-2025 MRP preparation period (select also the applicable segment)
Note on D9: The MRP Contact Person should be officially appointed by your organization's Senior Leadership/Board, and will be accountable as a main point of contact with IESO for all MRP preparation activities for that Market Organization.

## Checklist
|  | MRP Readiness Checklist for Market Participants |  |  |  |  | Version 1.0 |  | Hide Columns K to AO (only), Column J also has hidden text, in white font |  |  |  |  | Checklist Logic - should each row HIDE/SHOW, based on entries from Tab 1, that show here on row 3
Hide Row | [9 empty] | Logic Chart |  |  | Segment Name | ÿ Natural Gas/Oil Generator (dispatchable) | ÿ Natural Gas/Oil Generator (non-dispatchable) | ÿ Biogas/Biomass Generator (dispatchable) | ÿ Biogas/Biomass Generator (non-dispatchable) | ÿ Hydroelectric Generator (dispatchable) | ÿ Hydroelectric Generator (non-dispatchable) | ÿ Nuclear Generator(dispatchable) | ÿ Nuclear Generator (non-dispatchable) | ÿ Wind/Solar Generator (dispatchable) | ÿ Wind/Solar Generator (non-dispatchable) | ÿ Energy Storage Resource (dispatchable) | ÿ Energy Storage Resource (self-scheduling) | ÿ Local Distribution Company | ÿ Transmission Company | ÿ Dispatchable Load | ÿ Non Dispatchable Load | ÿ Hourly Demand Response | ÿ Intertie Trader (Imports and Exports) | ÿ Ancillary Service Provider | ÿ Transmission Rights Participant | ÿ Other Market Participant role | ÿ Price Responsive Load | ÿ Virtual Transaction Energy Trader | ÿ Adding a new Participation Segment or Resource during the 2023-2025 preparation period (check also the applicable segment)
Hide Row | Formating notes: sub-section titles are Bolded, Calibri 14, colour Gold Accent 4 - 40%, row height 34 | [7 empty] | All | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW |  |  | Segments Selected | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Hide Row | [8 empty] | All Dispatchable | GD,__,BD,__,HD,__,ND,__,RD,__,SD,__,__,__,DL,__,__,IT,__,__,__,__,__,__ |  |  |  | 1 | 4 | 7 | 10 | 13 | 16 | 19 | 22 | 25 | 28 | 31 | 34 | 37 | 40 | 43 | 46 | 49 | 52 | 55 | 58 | 61 | 64 | 67 | 70
[7 empty] | Click 'OK' here for Segment Filter Update-> |  | All Loads | __,__,__,__,__,__,__,__,__,__,__,__,LD,__,DL,NL,DR,__,__,__,__,PL,__,__ | Two Accuracy checks |  |  | GD | GN | BD | BN | HD | HN | ND | NN | RD | RN | SD | SS | LD | TR | DL | NL | DR | IT | AS | T2 | OT | PL | VT | NW
Task | Content | Objective | Action/ Testing/ Awareness | Recom-mended Timing to Address Task | Time Required for Task (Long/ Medium/ Short) | Task Progress (select option) | Market Segment(s) | SHOW | Use which Completed list? (Col H) | Segment Code for each Task | # of char=71 | code matches sub-codes
Hide Row | Cell for freeze frames |  |  | This is my Auto Hide row (see column J)- do not delete |  |  |  | HIDE
Getting Started with Market Renewal | [7 empty] | SHOW | [5 empty] | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Sign Up for IESO’s Market Renewal Program Newsletter | Sign-up at: www.ieso.ca/subscribe | Awareness for participants’ staff relating to all MRP training and activities | Action | Q2 2023 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Develop an Implementation Plan | Review this Readiness Checklist and Day-In-The-Life documentation | Identify a primary contact for MRP; Identify key resources to participate in testing and training efforts, and internal processes that need to be updated | Action | Q3 2023 | Medium | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Testing Connectivity to IESO Systems | [7 empty] | SHOW |  |  | 0 | not coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review the Connectivity Testing Test Plan | The Test Plan: [[future link to materials]] | Understanding of the activities, roles, and responsibilities during connectivity testing | Action | January 2024 | Long | Not Started | All (including a scaled back plan for LDCs,Transmitters, Non-Dispatchable Loads, and Other) | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review IT System Requirements | Review Participant Technical Reference Manual [[future link to materials]] | Confirmation that all hardware and software meets the IESO’s standards for MRP | Action | January 2024 | Medium | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Verify Application & Sandbox Access | Test links to IESO Tools [[future link to materials]] | Confirm access to IESO platforms, for users and API machine accounts | Action | January 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review Contact Roles and System Accesses | Review Online IESO information [[future link to Online IESO training guide]] | Confirm all contacts, users, and machine accounts have the right access roles and are ready for Market Trials | Action | Q2 2024 | Medium | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Authorization Process for Market Renewal | [7 empty] | SHOW |  |  | 0 | not coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
Alert MRP Team of intent to register as a Price Responsive Load or Virtual Transaction Energy Trader | Send e-mail to market.renewal@ieso.ca Select that Segment in your selections on Checklist's Intro tab to add more tasks | Provide a contact so IESO can follow up on readiness activities | Action | Q1 2024 | Short | Not Started | Virtual Traders, Price Responsive Loads | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,PL,VT,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No
If not a registered MP, begin Authorization Process | See website for an overview of process: https://www.ieso.ca/en/Sector-Participants/Connection-Process/Overview | Submit application to register as an IESO MP, and to register applicable new resources | Action | Q1 2024 | Long | Not Started | Virtual Traders, Price Responsive Loads, other new MPs | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,PL,VT,NW | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
Receive approval for above Application for Authorization to Participate | See website for an overview of process: https://www.ieso.ca/en/Sector-Participants/Connection-Process/Overview | Obtain approval on Application for Authorization | Action | Before Q2 2025 | Long | Not Started | Virtual Traders, Price Responsive Loads, other new MPs | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,PL,VT,NW | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
Review the “Becoming a Virtual Trader” Guide | Comprehensive information can be found here: [[future link to material]] | Understanding of the steps needed to participate | Action | October 2023 | Short | Not Started | Virtual Traders only | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,VT,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No
Review the “Becoming a Price Responsive Load” Guide | Comprehensive information can be found here: [[future link to material]] | Understanding of the steps needed to participate | Action | October 2023 | Short | Not Started | Price Responsive Loads, Electricity Storage (non-dispatchable) | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,SS,__,__,__,__,__,__,__,__,__,PL,__,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | Yes | No | No
Confirm Price Responsive Load's registration matches any linked Hourly Demand Response resource | Use [[future link to training guide]] | Conformity with Market Rules for Hourly Demand Response meeting physical Demand Response obligation through a Price Responsive Load | Action | Q1 2025 | Short | Not Started | Price Responsive Loads only | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,PL,__,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No
Preparation Steps for Registration, including Market Power Mitigation | [7 empty] | SHOW |  |  | 0 | not coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | No | No | No | Yes | Yes | Yes
Enter Market Control Entity information for each applicable resource | More information and instructions can be found here: [[future link to training guide for Market Control Entity]] | Understand, then provide, the required information on Market Control Entity | Awareness Action | Q4 2023 Q4 2024 | Short Medium | Not Started | Dispatchable Generators, Dispatchable Loads, PRL, Intertie Traders, Virtual Traders, Electricity Storage | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,SS,__,__,DL,__,__,IT,__,__,__,PL,VT,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | Yes | No | No | Yes | No | No | Yes | No | No | No | Yes | Yes | No
Review training material for awareness, and review Reference Level and Reference Quantity information in Online IESO | More information at: [[future link to Quick Take and Training Guide]] | Understand role of Reference Levels and Reference Quantities, and understand how to submit/review relevant information | Awareness Action | Q4 2023 Q4 2024 | Short Medium | Not Started | Dispatchable Generators (including Electricity Storage), Dispatchable Loads (for Operating Reserve only) Intertie Traders (Awareness Step Only) | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,__,__,__,DL,__,__,IT,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No
Assign a Market Power Mitigation Contact in Online IESO | Background educational material and step-by-step user guide [[future links to user guide]] | Required new contact role for all dispatchable participants | Action | Q4 2024 | Short | Not Started | Dispatchable Generators, Dispatchable Loads, Dispatchable Electricity Storage, and Intertie Traders | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,__,__,__,DL,__,__,IT,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No
Review Prudential Support Obligations in Online IESO | More information found here: [[future link to Quick Take and Training Guide]] | Understand how the price basis for Prudential Support is changing, and review collateral requirements | Awareness and Action | Prior to Q2 2025 MRP In-Service | Medium | Not Started | All (except Transmitters, Ancillary Services, TR holders and Other) | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,__,DL,NL,DR,IT,__,__,__,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | No | No | No | Yes | Yes | Yes
Post the Prudential Support for PRL and Virtual Traders | Training Guide: [[future link to Quick Take and Training Guide]] | Post the required prudential support for participation | Action | Q2 2025 | Medium | Not Started | Price Responsive Loads, Virtual Traders | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,PL,VT,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No
Review and enter new Registration Parameters for Hydroelectric Resources | Data Parameters List: [[future link]] How they will work: [[future link to Training Guide]] Testing Info: [[future link to Market Trials plan]] | Understand and be able to review/enter new resource parameters | Testing Action | Q3 2024 Q4 2024 | Short Short | Not Started | Hydroelectric Generators | SHOW | List 1 | __,__,__,__,HD,HN,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__ | 71 | coded correctly |  | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No
Review and enter new Thermal State Registration Parameters | Data Parameters List: [[future link]] How they will work: [[future link to Training Guide]] Testing Info: [[future link to Market Trials]] | Understand and be able to review/enter new resource parameters, like thermal states | Testing Action | Q3 2024 Q4 2024 | Medium Medium | Not Started | Gas/Oil/Bio-Gas/Biomass Generators | SHOW | List 1 | GD,GN,BD,BN,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No
Review and enter Registration Parameters for Pseudo Unit modelling, and Combustion Turbine allocations | Data Parameters List: [[future link]] How they will work: [[future link to Training Guide]] Testing Info: [[future link to Market Trials webpage for info]] | Understand how to elect for Pseudo Unit settlement and confirm resource parameters | Testing Action | Q3 2024 Q4 2024 | Medium Medium | Not Started | Gas/Oil/Bio-Gas/Biomass Generators | SHOW | List 1 | GD,GN,BD,BN,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No
Review and enter new Registration Parameters for Price Responsive Loads and Virtual Traders | Data Parameters List: [[future link]] How they will work: [[future link to Training Guide]] Testing Info: [[future link to Market Trials webpage for info]] | Understand and be able to review/enter new parameters | Testing Action | Q3 2024 Q4 2024 | Short Short | Not Started | Price Responsive Loads, Virtual Traders | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,PL,VT,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No
Review Generator Offer Guarantee training material | More information here: [[future link to training guide]] | Understand eligibility and settlement | Awareness | Q4 2023 | Medium | Not Started | NQS Generators (Gas/Oil/Bio-Gas/Biomass) | SHOW | List 1 | GD,__,BD,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No
Review Intertie Offer Guarantee training material | More information here: [[future link to training guide]] | Understand eligibility and settlement | Awareness | Q4 2023 | Medium | Not Started | Intertie Traders | SHOW | List 1 | __,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,IT,__,__,__,__,__,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No
Market Operations Preparation | [7 empty] | SHOW |  |  | 0 | not coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review details on changes to market processes and timing | More information Here: [[future link to Market Timing Graphic]] | Understand changes to market processes and timing, and make corresponding changes in MP business processes | Awareness | Q2 2024 | Medium | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Confirm “Energy Market Access Flag” for resources providing bids/offers | More information here: [[future link to User Guide]] | Requirement for dispatchable participant to verify | Awareness Action | Q3 2024 Q4 2024 | Short Short | Not Started | Generators, Electricity Storage, Dispatchable Loads, PRL, Hourly Demand Response, Intertie Traders, Virtual Traders | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,__,__,DL,__,DR,IT,__,__,__,PL,VT,__ | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | Yes | No | No | No | Yes | Yes | No
Review details on submitting forecasts into the Day-Ahead Market for Variable Generators | More information here: [[future link to the Training Guide]] | Review options for active versus passive Variable Generator participation in the renewed market | Testing Action | Q3 2024 Q4 2024 | Medium | Not Started | Dispatchable Wind/Solar Generators | SHOW | List 1 | __,__,__,__,__,__,__,__,RD,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__ | 71 | coded correctly |  | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No
Critical Task: Review and test revised IESO reports (MP to choose most relevant ones) | More information here: [[future link to Testing plan, and detail on batching]] Reports Location: [[future link to IESO Reports sandbox]] | Participants can review the sample and schema files for the many new and revised reports (public and private) | Action | From Q3 2023 through to 2024 testing period | Long | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Update MP’s API tools (if applicable) | Additional Resources: API Specs for EMI/MIM and Dispatch Services [[future link to IESO Reports]] | Prepare conforming changes to API (Application Programming Interface) accounts, update internal business processes | Action | Q2 2023 through to 2024 testing period | Long | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
System Testing and Market Trials for Market Participants | [7 empty] | SHOW |  |  | 0 | not coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Agree to terms for using testing tool for market trials | Review and agree to terms of use here: [[future Link to EULA agreement]] | Participants planning to test should review and accept terms for using test planning software | Action | Q2 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Critical Task: Participate in Market Trials for authorization and resource registration via Online IESO | Testing Webpage: [[future link to Market Trials test plan]] Test Plans: [[future Link to Test Plans]] | Testing to determine if MPs can enter new organization details in Online IESO | Testing | Q3 2024 | Long | Not Started | Dispatchable Generators, Dispatchable Loads, Electricity Storage, PRLs, Virtual Traders, Intertie Traders, Hourly Demand Response | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,SS,__,__,DL,__,DR,IT,__,__,__,PL,VT,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | Yes | No | No | Yes | No | Yes | Yes | No | No | No | Yes | Yes | No
Critical Task: Participate in Market Trials for submitting dispatch data into EMI/MIM | Testing Webpage: [[future link to Market Trials test plan] Test Plans: [[future link to Test Plans]] API Specs: for EMI/MIM | Test the systems for submitting bids/offers to EMI, including API Testing | Testing | Q3 2024 | Long | Not Started | Dispatchable Generators, Dispatchable Loads, Electricity Storage, PRLs, Virtual Traders, Hourly Demand Response, Intertie Traders | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,SS,__,__,DL,__,DR,IT,__,__,__,PL,VT,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | Yes | No | No | Yes | No | Yes | Yes | No | No | No | Yes | Yes | No
Critical Task: Participate in Market Trials for receiving dispatch instructions through Dispatch Service | Testing Webpage: [[future link to Market Trials test plan]] Test Plans: [[future link to Test Plan and training guides]] API Specs: for Dispatch Services | Test the systems for Dispatch Service, including API Testing | Testing | Q3 2024 | Long | Not Started | Dispatchable Generators, Dispatchable Loads, Electricity Storage, PRLs, Intertie Traders, Hourly Demand Response | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,SS,__,__,DL,__,DR,IT,__,__,__,PL,__,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | Yes | No | No | Yes | No | Yes | Yes | No | No | No | Yes | No | No
Critical Task: Participate in Market Trials for submitting new Settlements Form | Testing Webpage: [[future link to Market Trials test plan]] Test Plans: [[future link to Test Plan and training guides]] | Test if MP able to submit Fuel Cost Compensation claims, resulting from Generator Offer Guarantees (GOG) | Testing | Q3 2024 | Medium | Not Started | GOG-eligible NQS Generators only (gas/oil/bio-gas/biomass) | SHOW | List 1 | GD,__,BD,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No
Critical Task: Participate in End-to-End Testing of business processes and tools | Testing Webpage: [[future link to Market Trials test plan]] Test Plans: [[future link to Test Plan and training guides]] | Open-ended testing for the flow of data and integration of systems from beginning to end | Testing | Q1 2025 | Long | Not Started | Dispatchable Generators, Dispatchable Loads, Electricity Storage, PRLs, Virtual Traders, Intertie Traders, Hourly Demand Response | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,SS,__,__,DL,__,DR,IT,__,__,__,PL,VT,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | Yes | No | No | Yes | No | Yes | Yes | No | No | No | Yes | Yes | No
Training and Education for Market Participant Staff | [7 empty] | SHOW | List 1 |  | 0 | not coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review registration-related training materials | Overview: [[future link to MRP training summary/guides]] | Understanding of registration activities, like prudential review, registering Market Power Mitigation related data, etc. | Awareness | Q1 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review training on price formation | [[future link to training guide]] | Fully understand how new pricing structures will work | Awareness | Q2 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review training on Economic Operating Point and Make-Whole Payments | [[future link to training guide]] | Understand how EOP and MWP work in the renewed markets | Awareness | Q2 2024 | Short | Not Started | Dispatchable MPs | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,__,__,__,DL,__,__,IT,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No
Review training on Market Power Mitigation (MPM) | [[future link to training guides]] | Understand how conduct and impact tests work, designation of constrained areas, etc. | Awareness | Q2 2024 | Short | Not Started | Dispatchable Generators, Dispatchable Loads, Electricity Storage, Intertie Traders, PRL, Virtual Traders | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,SS,__,__,DL,__,__,IT,__,__,__,PL,VT,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | Yes | No | No | Yes | No | No | Yes | No | No | No | Yes | Yes | No
Review training on Settlement Statements and Invoicing | [[future link to training guide, charge types]] | Understanding settlements in the renewed market | Awareness | Q2 2024 | Medium | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review training on the Enhanced Pre-Dispatch Optimization | [[future link to training guide]] | Understand how the IESO’s optimization functions work | Awareness | Q2 2024 | Short | Not Started | Dispatchable MPs | SHOW | List 1 | GD,__,BD,__,HD,__,ND,__,RD,__,SD,__,__,__,DL,__,__,IT,__,__,__,__,__,__ | 71 | coded correctly |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No
Review training materials for new registration and dispatch parameters | Overview: [[future link to MRP training summary/guides]] | Understanding of new data parameters, like hydro and pseudo-unit modelling, etc. | Awareness | Q2 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review training materials for daily operations | Overview: [[future link to MRP training summary/guides]] | Understanding of daily market processes, availability declaration envelope, entering, submitting, revising bids and offers, etc. | Awareness | Q2 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review training materials for pricing | Overview: [[future link to MRP training summary/guides]] | Understanding of market structures affecting pricing, like administrative pricing, congestion rents, etc. | Awareness | Q3 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Review training materials for market outputs and reporting | Overview: [[future link to MRP training summary/guides]] | Understanding of reporting of market outcomes | Awareness | Q4 2024 | Short | Not Started | All | SHOW | List 1 | GD,GN,BD,BN,HD,HN,ND,NN,RD,RN,SD,SS,LD,TR,DL,NL,DR,IT,AS,T2,OT,PL,VT,NW | 71 | coded correctly |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Note on F6: The dates shown here below, indicate an ideal time-period to ensure this work is completed within, and do not represent a deadline, but simply provide a guide to ensure that you are on-schedule with your peers.
Note on G6: While the actual ‘Time Required’ may vary widely depending on an Organization’s size or complexity, tasks marked ‘Short’ are generally estimated to take hours or less, those marked ‘Medium’ may involve multiple days, and those marked ‘Long’ could span weeks or longer.
Note on H6: Selecting 'Complete' indicates that all aspects of this task have been completed, for all IT systems, and impacted individuals within your organization and your related vendors, covering all applicable human and machine accounts for each of your Market Resources. It does not refer only to the single User of this Checklist.

## Disclaimers
Accessibility Disclaimer
This is a locked, fillable form and not all of the content in this document may be captured by a screen-reading device. If you require additional assistance to complete and submit this form, please contact Market.Renewal@ieso.ca
AN IESO MARKETPLACE TRAINING PUBLICATION
This guide has been prepared to assist in the IESO training of market participants. Users of this guide are reminded that they remain responsible for complying with all of their obligations under the market rules and associated policies, standards and procedures relating to the subject matter of this guide, even if such obligations are not specifically referred to herein. While every effort has been made to ensure that any extracts from the market rules or other documents in this guide are accurate and up to date, users must be aware that the specific provisions of the market rules or particular document posted on the web site of Ontario’s Independent Electricity System Operator shall govern.

## Dropdowns (hidden)
Dropdown List#1 |  | Dropdown List #2 | Dropdown List #3
Not Started |  | Not Started | No
In Progress |  | Reviewed & Not Interested | Yes
Complete |  | Reviewed & Interested | Does Not Apply
Does Not Apply
Developer's Note: dropdown list #1 is currently the only one in use, by this checklist, in order to keep it simple and consistent for users, and to streamline transfer into Online IESO.