## Key Calendar Dates
Key Calendar Dates for End-to-End Testing
Week # | Scenario No. and Scenario Name | Scenario Schedule | Test Scenario | Impacted Trade Date | MPs Submit Dispatch Data On | DAM Run | Prerequisite(s)
Week 1 | S11 - 1-Day Advance Approval Outage | Jan 20 - Jan 22 | S11-TC01 (1-DAY AA) | 2025-01-21 | 2025-01-17 | N/A | Market participant to submit the outage request for an equipment by 10:00 EST on Jan 17 for the Jan 21 trade date, and provide the following details: 1. Outage slip entered 2. Whether the MP wishes for the IESO to approve or reject the outage
|  |  |  | 2025-01-22 | 2025-01-20 | N/A | Market Participant to submit the outage request for an equipment by 10:00 EST on Jan 20 for the Jan 22 trade date, and provide the following details: 1. Outage slip entered 2. Whether the MP wishes for the IESO to approve or reject the outage
|  |  | S11-TC02 (1-DAY AA) | 2025-01-21 | 2025-01-17 | N/A | Market Participant to submit the outage request for an equipment by 10:00 EST on Jan 17 for the Jan 21 trade date, and provide the following details: 1. Outage slip entered 2. MP will notify the IESO via email to leave the outage request alone for it to be automatically rejected.
|  |  |  | 2025-01-22 | 2025-01-20 | N/A | Market Participant to submit the outage request for an equipment by 10:00 EST on Jan 20 for the Jan 22 trade date, and provide the following details: 1.Outage slip entered 2. MP will notify the IESO via email to leave the outage request alone for it to be automatically rejected.
| S17 - GOG Commitment Advancements and Extensions | Jan 20 - Jan 23 | S17-TC01 (DAM Timeframe) | 2025-01-21 | 2025-01-20 | 2025-01-20
|  |  |  | 2025-01-22 | 2025-01-21 | 2025-01-21
|  |  |  | 2025-01-23 | 2025-01-22 | 2025-01-22
|  |  | S17-TC02 (PD Timeframe) | 2025-01-20 | 2025-01-20 | N/A
|  |  |  | 2025-01-21 | 2025-01-21 | N/A
|  |  |  | 2025-01-22 | 2025-01-22 | N/A
|  |  |  | 2025-01-23 | 2025-01-23 | N/A
| S21 - SEAL Constraint | Jan 21 - Jan 22 | S21-TC01 (PD Timeframe) | 2025-01-22 | 2025-01-21 | N/A | Market Participant to provide the following details to the IESO by EOD of Jan 21 to test this scenario for the Jan 22 trade date: - Resource to be constrained - What timeframe would the constraints be applicable for (if it is for RT only) - Whether to constrain up, down, or to a fixed value - Specific hour(s) if applicable
Week 2 | S12 - Hourly Demand Response - HDR Activation | Jan 27-Jan 29 | S12-TC01 (DAM Timeframe) | 2025-01-28 | 2025-01-27 | 2025-01-27 | Market Participant to provide IESO the below details by EOD Jan 24 to test this scenario for the Jan 28 trade date: - Resource name - Hours of activation
|  |  |  | 2025-01-29 | 2025-01-28 | 2025-01-28 | Market Participant to provide IESO the below details by EOD Jan 27 to test this scenario for the Jan 29 trade date: - Resource name - Hours of activation
| S13 - Operating Reserve (OR) Activation | Jan 28 | S13-TC01 (PD Timeframe) | 2025-01-28 | 2025-01-27 | N/A | Market Participant should provide the following details to the IESO by EOD Jan 27 to test this scenario for the Jan 28 trade date: - Resource name - Hour of activation Note(s): - Activation will last at least 15 minutes. - The IESO cannot guarantee the activation of specific MW amounts due to the co-optimization and scheduling of operating reserve.
| S18 - GOG Commitment Withdrawn by MP with more than 4 hours advance notice | Jan 27 - Jan 30 | S18-TC01 (DAM Timeframe) | 2025-01-28 | 2025-01-27 | 2025-01-27 | Market Participant should provide the following details to the IESO by EOD Jan 27 to test this scenario for the Jan 28 trade date: - Resource to have commitment withdrawn
|  |  |  | 2025-01-29 | 2025-01-28 | 2025-01-28 | Market Participant should provide the following details to the IESO by EOD Jan 28 to test this scenario for the Jan 29 trade date: -Resource to have commitment withdrawn
|  |  |  | 2025-01-30 | 2025-01-29 | 2025-01-29 | Market Participant should provide the following details to the IESO by EOD Jan 29 to test this scenario for the Jan 30 trade date: -Resource to have commitment withdrawn
| S19 - GOG Commitment Withdrawn by MP with less than 4 hours advance notice | Jan 27 - Jan 30 | S19 - TC01 (DAM Timeframe) | 2025-01-28 | 2025-01-27 | 2025-01-27 | Market Participant should provide the following details to the IESO by EOD Jan 27 to test this scenario for the Jan 28 trade date: -Resource to have commitment withdrawn
|  |  |  | 2025-01-29 | 2025-01-28 | 2025-01-28 | Market Participant should provide the following details to the IESO by EOD Jan 28 to test this scenario for the Jan 29 trade date: -Resource to have commitment withdrawn
|  |  |  | 2025-01-30 | 2025-01-29 | 2025-01-29 | Market Participant should provide the following details to the IESO by EOD Jan 29 to test this scenario for the Jan 30 trade date: -Resource to have commitment withdrawn
|  |  | S19 - TC02 (PD Timeframe) | 2025-01-28 | 2025-01-27 | N/A | Market Participant should provide the following details to the IESO by EOD Jan 27 to test this scenario for the Jan 28 trade date: - Resource to have commitment withdrawn
|  |  |  | 2025-01-29 | 2025-01-28 | N/A | Market Participant should provide the following details to the IESO by EOD Jan 28 to test this scenario for the Jan 29 trade date: - Resource to have commitment withdrawn
|  |  |  | 2025-01-30 | 2025-01-29 | N/A | Market Participant should provide the following details to the IESO by EOD Jan 29 to test this scenario for the Jan 30 trade date: - Resource to have commitment withdrawn
| S17 - GOG Commitment Advancements and Extensions | Jan 27 - Jan 30 | S17-TC01 (DAM Timeframe) | 2025-01-28 | 2025-01-27 | 2025-01-27
|  |  |  | 2025-01-29 | 2025-01-28 | 2025-01-28
|  |  |  | 2025-01-30 | 2025-01-29 | 2025-01-29
|  |  | S17-TC02 (PD Timeframe) | 2025-02-27 | 2025-02-27 | N/A
|  |  |  | 2025-01-28 | 2025-01-28 | N/A
|  |  |  | 2025-01-29 | 2025-01-29 | N/A
|  |  |  | 2025-01-30 | 2025-01-30 | N/A
Week 3 | S2-DAM Failure | Feb 3 - Feb 4 | S2-TC01 (DAM Timeframe) | 2025-02-04 | 2025-02-03 | 2025-02-03
| S16 - GOG Commitment Terminated by the IESO | Feb 3 - Feb 5 | S16-TC01 (DAM Timeframe) | 2025-02-04 | 2025-02-03 | 2025-02-03 | Note: This scenario cannot be tested for the Feb 4 trade date as DAM will be failed by the IESO.
|  |  |  | 2025-02-05 | 2025-02-04 | 2025-02-04 | Market Participant should provide the following details to the IESO by EOD on Feb 3 to test this scenario for the Feb 5 trade date: - Resource - Dispatch date and time
| S5 - Make-Whole Payment | Feb 3 - Feb 5 | S5-TC01 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | Note: As DAM will be failed on Feb 04, this scenario cannot be tested for the date when DAM is scheduled to run (Feb 4). Market Participant should provide the following details to the IESO by EOD on Feb 3 to test this scenario for the Feb 5 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  | S5-TC02 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 3 to test this scenario for the Feb 4 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 4 to test this scenario for the Feb 5 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  | S5-TC03 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | Note: As DAM will be failed on Feb 4, this scenario cannot be tested for the date when DAM is scheduled to run (Feb 4). Market Participant should provide the following details to the IESO by EOD on Feb 3 to test this scenario for the Feb 5 trade date: - Resource to be constrained with reliability constraint (DARCMT) - Dispatch date and time
|  |  | S5-TC04 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 3 to test this scenario for the Feb 4 trade date: - Resource to be constrained with reliability constraint (PDRCMT) - Dispatch date and time
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 4 to test this scenario for the Feb 5 trade date: - Resource to be constrained with reliability constraint (PDRCMT) - Dispatch date and time
| S7 - Market Power Mitigation | Feb 3- Feb 5 | S7-TC01 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | Note: As DAM will be failed on Feb 4, this scenario cannot be tested for the date when DAM is scheduled to run (Feb 4). 1. Reference level values exist in the system for the selected resource 2. Market Participants should provide the following details to the IESO by Jan 31 12:00 EST for week 3 testing: - Resource(s) that they would like to be added to a Narrow Constrained Area (NCA)
|  |  | S7-TC02 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | 1. Reference level values exist in the system for the selected resource 2. Market Participants should provide the following details to the IESO by Jan 31 12:00 EST for week 3 testing: - Resource(s) that they would like to be added to a Narrow Constrained Area (NCA)
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | 1. Reference level values exist in the system for the selected resource 2. Market Participants should provide the following details to the IESO by Jan 31 12:00 EST for week 3 testing: - Resource(s) that they would like to be added to a Narrow Constrained Area (NCA)
|  |  | S7-TC03 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA testing condition
|  |  | S7-TC04 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA testing condition
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA testing condition
|  |  | S7-TC05 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | 1. Reference level values exist in the system for the selected resource
|  |  | S7-TC06 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | 1. Reference level values exist in the system for the selected resource
|  |  | S7-TC07 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | 1. Reference level values exist in the system for the selected resource
|  |  | S7-TC08 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted energy offer up to MLP, and start-up offer and speed no-load offer exceeding conduct thresholds
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted energy offer up to MLP, and start-up offer and speed no-load offer exceeding conduct thresholds
|  |  | S7-TC09 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | Note: As DAM will be failed on Feb 4, this scenario cannot be tested for the date when DAM is scheduled to run (Feb 4). Market Participant should provide the following details to the IESO by EOD on Feb 03 to test this scenario for the Feb 5 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  | S7-TC10 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 3 to test this scenario for the Feb 4 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 4 to test this scenario for the Feb 5 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
| S22 - Market Power Mitigation (MPM) Global Threshold | Feb 4 - Feb 5 | S22- TC01 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  | S22- TC02 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  | S22- TC03 (DAM Timeframe) | 2025-02-05 | 2025-02-04 | 2025-02-04 | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
|  |  | S22- TC04 (PD Timeframe) | 2025-02-04 | 2025-02-03 | N/A | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
|  |  |  | 2025-02-05 | 2025-02-04 | N/A | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
| S17 - GOG Commitment Advancements and Extensions | Feb 3 - Feb 5 | S17-TC01 (DAM Timeframe) | 2025-02-04 | 2025-02-03 | 2025-02-03 | Note: This scenario cannot be tested for the Feb 4 trade date as DAM will be failed by the IESO.
|  |  |  | 2025-02-05 | 2025-02-04 | 2025-02-04
|  |  | S17-TC02 (PD Timeframe) | 2025-02-03 | 2025-02-03 | N/A
|  |  |  | 2025-02-04 | 2025-02-04 | N/A
|  |  |  | 2025-02-05 | 2025-02-05 | N/A
Week 4 (High Demand) | S5 - Make-Whole Payment | Feb 11 - Feb 14 | S5-TC01 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10 | Market Participant should provide the following details to the IESO by EOD on Feb 7 to test this scenario for the Feb 11 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11 | Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 12 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 13 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 14 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  | S5-TC02 (PD Timeframe) | 2025-02-11 | 2025-02-10 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 11 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  |  | 2025-02-12 | 2025-02-11 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 12 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 13 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 13 to test this scenario for the Feb 14 trade date: - Resource to be constrained with reliability constraint (REL) - Dispatch date and time
|  |  | S5-TC03 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10 | Market Participant should provide the following details to the IESO by EOD on Feb 7 to test this scenario for the Feb 11 trade date: - Resource to be constrained with reliability constraint (DARCMT) - Dispatch date and time
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11 | Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 12 trade date: - Resource to be constrained with reliability constraint (DARCMT) - Dispatch date and time
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 13 trade date: - Resource to be constrained with reliability constraint (DARCMT) - Dispatch date and time
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 14 trade date: - Resource to be constrained with reliability constraint (DARCMT) - Dispatch date and time
|  |  | S5-TC04 (PD Timeframe) | 2025-02-11 | 2025-02-10 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 11 trade date: - Resource to be constrained with reliability constraint (PDRCMT) - Dispatch date and time
|  |  |  | 2025-02-12 | 2025-02-11 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 12 trade date: - Resource to be constrained with reliability constraint (PDRCMT) - Dispatch date and time
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 13 trade date: - Resource to be constrained with reliability constraint (PDRCMT) - Dispatch date and time
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 13 to test this scenario for the Feb 14 trade date: - Resource to be constrained with reliability constraint (PDRCMT) - Dispatch date and time
| S7 - Market Power Mitigation | Feb 11- Feb 14 | S7-TC01 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10 | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 7 to test this scenario for the Feb 11 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11 | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 12 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 13 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 14 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  | S7-TC02 (PD Timeframe) | 2025-02-11 | 2025-02-10 | N/A | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 11 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  |  | 2025-02-12 | 2025-02-11 | N/A | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 12 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 13 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | 1. Reference level values exist in the system for the selected resource 2. Market Participant should provide the following details to the IESO by EOD on Feb 13 to test this scenario for the Feb 14 trade date: - Resource which Market Participants would like to be added to a Narrow Constrained Area (NCA)
|  |  | S7-TC03 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10 | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11 | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  | S7-TC04 (PD Timeframe) | 2025-02-11 | 2025-02-10 | N/A | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  |  | 2025-02-12 | 2025-02-11 | N/A | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | 1. Reference level values exist in the system for the selected resource 2. Resource's congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | 1.Reference Level values exist in the system for the selected resource 2.Resource's Congestion component of LMP should be greater $25/MWh to meet BCA Testing Condition
|  |  | S7-TC05 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10 | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11 | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | 1. Reference level values exist in the system for the selected resource
|  |  | S7-TC06 (PD Timeframe) | 2025-02-11 | 2025-02-10 | N/A | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-12 | 2025-02-11 | N/A | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | 1. Reference level values exist in the system for the selected resource
|  |  | S7-TC07 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10 | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11 | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | 1. Reference level values exist in the system for the selected resource
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | 1. Reference level values exist in the system for the selected resource
|  |  | S7-TC08 (PD Timeframe) | 2025-02-11 | 2025-02-10 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted energy offer up to MLP, and start-up offer and speed no-load offer exceeding conduct thresholds
|  |  |  | 2025-02-12 | 2025-02-11 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted energy offer up to MLP, and start-up offer and speed no-load offer exceeding conduct thresholds
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted energy offer up to MLP, and start-up offer and speed no-load offer exceeding conduct thresholds
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted energy offer up to MLP, and start-up offer and speed no-load offer exceeding conduct thresholds
|  |  | S7-TC09 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10 | Market Participant should provide the following details to the IESO by EOD on Feb 7 to test this scenario for the Feb 11 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11 | Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 12 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 13 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 14 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  | S7-TC10 (PD Timeframe) | 2025-02-11 | 2025-02-10 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 10 to test this scenario for the Feb 11 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  |  | 2025-02-12 | 2025-02-11 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 11 to test this scenario for the Feb 12 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 12 to test this scenario for the Feb 13 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | Market Participant should provide the following details to the IESO by EOD on Feb 13 to test this scenario for the Feb 14 trade date: - Resource to participate in Local Market Power for Operating Reserve (RLOCAL) test.
| S22- Market Power Mitigation (MPM) Global Threshold | Feb 12 - Feb 14 | S22- TC01 (DAM Timeframe) | 2025-02-12 | 2025-02-11 | 2025-02-11 | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  | S22- TC02 (PD Timeframe) | 2025-02-12 | 2025-02-11 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | 1. Reference level values exist in the system for the selected resource 2. Submitted resource's 10S/10N/30R LMP > $15, where resource MAX reserve area is not binding
|  |  | S22- TC03 (DAM Timeframe) | 2025-02-12 | 2025-02-11 | 2025-02-11 | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12 | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13 | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
|  |  | S22- TC04 (PD Timeframe) | 2025-02-12 | 2025-02-11 | N/A | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
|  |  |  | 2025-02-13 | 2025-02-12 | N/A | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
|  |  |  | 2025-02-14 | 2025-02-13 | N/A | 1. Reference level values exist in the system for the selected resource 2. Condition needed to test Energy Global Market Power: "IBP> $100 AND [extCong is negative; OR NISL shadow price is negative]
| S17 - GOG Commitment Advancements and Extensions | Feb 11- Feb 14 | S17-TC01 (DAM Timeframe) | 2025-02-11 | 2025-02-10 | 2025-02-10
|  |  |  | 2025-02-12 | 2025-02-11 | 2025-02-11
|  |  |  | 2025-02-13 | 2025-02-12 | 2025-02-12
|  |  |  | 2025-02-14 | 2025-02-13 | 2025-02-13
|  |  | S17-TC02 (PD Timeframe) | 2025-02-11 | 2025-02-11 | N/A
|  |  |  | 2025-02-12 | 2025-02-12 | N/A
|  |  |  | 2025-02-13 | 2025-02-13 | N/A
|  |  |  | 2025-02-14 | 2025-02-14 | N/A
Week 5 (High Demand) | S14 - OR Shortfall | Feb 19 - Feb 20 | S14-TC01 (DAM Timeframe) | 2025-02-19 | 2025-02-18 | 2025-02-18
|  |  |  | 2025-02-20 | 2025-02-19 | 2025-02-19
| S20 - GOG Commitment Performance Failure | Feb 18 - Feb 20 | S20-TC01 (DAM Timeframe) | 2025-02-18 | 2025-02-17 | 2025-02-17 | Note: This scenario can be tested for the given trade date if there is standing data available. MP should not submit dispatch data on Feb 17 as it is a holiday.
|  |  |  | 2025-02-19 | 2025-02-18 | 2025-02-18
|  |  |  | 2025-02-20 | 2025-02-19 | 2025-02-19
| S24 - OR Clawback | Feb 19 - Feb 20 | S24-TC01 (PD Timeframe) | 2025-02-19 | 2025-02-18 | N/A
|  |  |  | 2025-02-20 | 2025-02-19 | N/A
| S17 - GOG Commitment Advancements and Extensions | Feb 18 - Feb 20 | S17-TC01 (DAM Timeframe) | 2025-02-18 | 2025-02-17 | 2025-02-17 | Note: This scenario can be tested for the given trade date if there is standing data available. MP should not submit dispatch data on Feb 17 as it is a holiday.
|  |  |  | 2025-02-19 | 2025-02-18 | 2025-02-18
|  |  |  | 2025-02-20 | 2025-02-19 | 2025-02-19
|  |  | S17-TC02 (PD Timeframe) | 2025-02-18 | 2025-02-18 | N/A
|  |  |  | 2025-02-19 | 2025-02-19 | N/A
|  |  |  | 2025-02-20 | 2025-02-20 | N/A
Week 6 (Low Demand) | S23 - Major Outage - EW Tie Binding | Feb 24 - Feb 25 | S23-TC01 (DAM-Timeframe) | 2025-02-25 | 2025-02-24 | 2025-02-24
| S8--Intertie Curtailment | Feb 25 - Feb 27 | S8-TC01 (DAM Timeframe) | 2025-02-26 | 2025-02-25 | 2025-02-25 | Market Participant to send an email to the IESO with the following details by EOD Feb 25 to test this scenario for the Feb 26 trade date: - Resource/transaction to have curtailed - Mid-hour or full-hour curtailment - Specific hour(s) if applicable Note: MPs can specify the curtailment code and type if they desire
|  |  |  | 2025-02-27 | 2025-02-26 | 2025-02-26 | Market Participant to send an email to the IESO with the following details by EOD Feb 26 to test this scenario for the Feb 27 trade date: - Resource/transaction to have curtailed - Mid-hour or full-hour curtailment - Specific hour(s) if applicable Note: MPs can specify the curtailment code and type if they desire
| S26 - Capacity Flag - Export/Import | Feb 25 - Feb 26 | S26-TC01 (DAM Timeframe) | 2025-02-26 | 2025-02-25 | 2025-02-25 | Market Participant to provide the following details to the IESO by Feb 24 to test this scenario for the Feb 26 trade date: - Transaction to be called - Specific hour(s) if applicable
| S17 - GOG Commitment Advancements and Extensions | Feb 24 - Feb 27 | S17-TC01 (DAM Timeframe) | 2025-02-25 | 2025-02-24 | 2025-02-24
|  |  |  | 2025-02-26 | 2025-02-25 | 2025-02-25
|  |  |  | 2025-02-27 | 2025-02-26 | 2025-02-26
|  | Feb 24 - Feb 27 | S17-TC02 (PD Timeframe) | 2025-02-24 | 2025-02-24 | N/A
|  |  |  | 2025-02-25 | 2025-02-25 | N/A
|  |  |  | 2025-02-26 | 2025-02-26 | N/A
|  |  |  | 2025-02-27 | 2025-02-27 | N/A
Week 7
****End-to-End Testing Paused****
Week 8 | E2E Retest | TBD | TBD | 2025-03-10 | TBD | TBD
|  | TBD | TBD | 2025-03-11 | TBD | TBD
|  | TBD | TBD | 2025-03-12 | TBD | TBD
|  | TBD | TBD | 2025-03-13 | TBD | TBD
| S27 - Resettlement Statement | 2025-03-14 | S27-TC01 | Jan 20 - Jan 31 | _ |  | On Mar 14, RCSS1 settlement statements are generated for the trade dates between Jan 20, 2025 and Jan 31, 2025.
Week 9 | E2E Retest | TBD | TBD | 2025-03-17 | TBD | TBD
|  | TBD | TBD | 2025-03-18 | TBD | TBD
|  | TBD | TBD | 2025-03-19 | TBD | TBD
|  | TBD | TBD | 2025-03-20 | TBD | TBD
|  | TBD | TBD | 2025-03-21 | TBD | TBD
Week 10 | E2E Retest | TBD | TBD | 2025-03-17 | TBD | TBD
|  | TBD | TBD | 2025-03-18 | TBD | TBD
|  | TBD | TBD | 2025-03-19 | TBD | TBD